## Sheet1
Group Code | Student 1 Name | Student 1 ID | Student 2 Name | Student 2 ID | Student 3 Name | Student 3 ID | Student 4 Name | Student 4 ID | Topic | Project Proposal | Meeting Link | Meeting 1 (9 Nov) | Status | Meeting 2 (16 Nov) | Status | Meeting 3 (23 Nov) | Meeting 4 (30 Nov) | Meeting 5 (7 Dec) | Meeting 6 (28 Dec) | Final Demonstration | Final Report
1 | H.M. Basharat Ziad | 1721155042 | Sharmin Akter Mukti | 1831029642 | Nishat Tamanna | 1811569642 |  |  | Cosmetics Shop(App) | TRUE | https://meet.google.com/pdj-ujcm-wqc | TRUE | Learning Phase. Progress acceptable | TRUE | Learning Phase. Progress acceptable. Showed a demo app. | No meeting this week. Please send me an email explaining your progress. Thank you | TRUE | TRUE | TRUE | 2022-01-13 15:00 | Final Report Due Saturday 5:00 pm
2 | Md Toufique Husein | 1921750642 | Nazmoon Nahar Punom | 1922049042 |  |  |  |  | Online Library/ E-Learning(Website) | TRUE | https://meet.google.com/nkc-yafw-sez | TRUE | Learning Phase (django). Progress acceptable | TRUE | Learning (Backend) almost done. Progress acceptable |  | TRUE | TRUE | TRUE | 2022-01-13 15:15
3 | Sakibur Rahman Khan | 1811185642 | Nawar Anbar Fahim | 1911222042 | Md.Riyad-Ur-Rahman | 1911125642 | Abrar Shahriar | 1911187642 | Hospital Management System | TRUE | https://meet.google.com/zfn-wgpz-tpq | TRUE | Learning Phase (javascript). Progress acceptable | TRUE | Learning Phase. Progress acceptable. Planning of Database is done. |  | TRUE | TRUE | TRUE | 2022-01-13 15:30
4 | Sabbir Hossain | 1712312642 | Laisul Morshed | 1813500642 |  |  |  |  | Healthcare Website: Blood Bank Management | TRUE | https://meet.google.com/zrs-yhqn-nkw | TRUE | Learning Phase (github), Basic Login page ready. Progess acceptable. | TRUE | Learning Phase. |  | TRUE | TRUE | FALSE | 2022-01-13 15:45
5 | Md.Alvi Islam Dipta | 1811033642 | Fahian Oishy | 1911129642 |  |  |  |  | Healthy Diet App | TRUE | https://meet.google.com/ckh-dazy-roj | TRUE | Learning Phase (android studio). Progress acceptable. | TRUE | Learning Phase. Progress acceptable |  | FALSE | TRUE | FALSE | 2022-01-13 16:00
6 | R Rafi Hossain | 1811578042 | [6 empty] | Doctor Info and Appointment (website) | TRUE | https://meet.google.com/jck-vvkq-dir | TRUE | Progress Sufficient. | TRUE | Will show progress next week. |  | FALSE | TRUE | TRUE | 2022-01-13 16:15
7 | Md Abu Zobair | 1911447642 | Mashrur Tauhid | 1911006642 |  |  |  |  | Shoes store(website) | TRUE | https://meet.google.com/gxm-datf-ext | TRUE | Basic login page ready (using HTML). Progress Sufficient. | TRUE | Learning Phase (bootstrap). Progress acceptable. |  | TRUE | TRUE | TRUE | 2022-01-13 16:30
8 | Adnan Shishir | 1711337042 | Sadia Iqbal | 1713008042 |  |  |  |  | Online Voting System Application | TRUE | https://meet.google.com/jmw-guks-vqm | TRUE | Database design ready. Learning Phase (django) Progress acceptable. | TRUE | Showed a demo Website. Progress acceptable. |  | TRUE | TRUE | TRUE | 2022-01-13 16:45
9 | Md. Mahbubur Rahman | 1711047642 | Ananya Saha | 1731092042 | Md.Ridwanul Islam | 1812608642 |  |  | Online Food Delivery | TRUE | https://meet.google.com/joz-xzjo-pud | TRUE | Learning Phase (firebase). Progress acceptable | TRUE | Learning Phase. Progress acceptable |  | TRUE | TRUE | FALSE | 2022-01-13 17:00
10 | Farzan Noor Chowdhury | 2012136642 | [6 empty] | Online Service platform (website) | TRUE | https://meet.google.com/cye-bpcv-xkh | TRUE | Learning Phase (javascript). Progress acceptable | TRUE | Learning Phase (React, json). Progress acceptable |  | TRUE | FALSE | FALSE | 2022-01-13 17:15
11 | Md.Shariful Islam | 1530655042 | Sadik Munha | 1931437042 |  |  |  |  | Ticket Booking System | TRUE | https://meet.google.com/djj-jtbs-ckb | TRUE | Learning Phase. Progress acceptable | TRUE | Started working on code. Progress acceptable |  | FALSE | FALSE | TRUE | 2022-01-13 17:30
12 | Nowshin Nawal Mim | 1911054042 | [6 empty] | Online Examination System | TRUE | https://meet.google.com/rfy-ommf-piv | TRUE | Learning Phase. Will show progress next week. | TRUE | Showed a demo Website. Progress acceptable. |  | FALSE | TRUE | TRUE | 2022-01-13 17:45
13 | Md. Jafor Sadek | 1931469042 | [6 empty] | Fitness android app | TRUE | https://meet.google.com/nek-eayh-vkj | TRUE | Learning Phase. Will show progress next week. | TRUE | Learning Phase. Progress acceptable. Showed a demo app. |  | FALSE | TRUE | TRUE | 2022-01-13 18:00